GWI Data Lake Migration

Athena SQL to Glue PySpark Notebooks

New Account  |  No Cross-Account Connectivity

5 Sources  |  4 Phases  |  683 Total Hours  |  17 Weeks  |  2 Resources

# Executive Summary

All 5 data sources are migrated from Athena SQL views/CTAS to Glue PySpark notebooks in a completely new AWS account. No Athena is used. No cross-account connectivity exists. Each notebook reads raw data from S3, transforms it, and writes Parquet to the new curated S3 bucket.

| Source | Phase 1 (Infra) | Phase 2 (Curated) | Phase 3 (SSOT) | Phase 4 (Validate) | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Gaiia | 18h | 87h | 61h | 14h | 180h |
| Intacct | 18h | 59h | 78h | 13h | 168h |
| Vetro | 11h | 58h | 53h | 11h | 133h |
| Salesforce | 11h | 45h | 58h | 10h | 124h |
| Platt | 7h | 30h | 33h | 8h | 78h |
| TOTAL | 65h | 279h | 283h | 56h | 683h |

## Key Principles

- New Account: Everything is built fresh. No updates to old account infrastructure.

- No Athena: All Athena SQL views and CTAS are converted to Glue PySpark notebooks.

- No Cross-Connectivity: Old and new accounts are completely separate. No cross-account IAM roles, no data comparison across accounts.

- Curated Output: All PySpark notebooks write Parquet to a new curated S3 bucket and register tables in Glue Catalog.

- Gaiia Only: Gaiia is the only source with S3 folder structure changes (3 tenants, new partition scheme). All other sources retain existing folder structures.

## Cross-Source Dependencies (Crosswalks)

Crosswalk tables map the same real-world entity across different source systems using their different IDs, linking them to a unified SSOT ID.

| Crosswalk | Source A | Source B | Link Field |
| --- | --- | --- | --- |
| Gaiia-Platt | Gaiia accounts | Platt customers | plat_id custom field |
| Gaiia-Vetro | Gaiia accounts | Vetro plans | vetro_id custom field |
| Platt-Intacct | Platt customers | Intacct GL entries | platt_to_intacct_customer_1to1 |
| SF-Intacct | Salesforce accounts | Intacct GL entries | SF-Intacct crosswalk files |
| SF-Platt | Salesforce accounts | Platt customers | Guarantor mappings |

# 1. GAIIA

Gaiia is the most complex source due to S3 folder structure changes and multi-tenant support (gwi / lymefiber / dvfiber). Other sources do not have folder structure changes.

Old Path (old account): s3://gwi-raw-us-east-2-pc/raw/gaiia/graphql/{entity}/tenant={t}/dt={d}/

New Path (new account): s3://macmountain-dl-raw-us-east-1-.../{tenant}/gaiia/network/{entity}/ingestion_year=.../

## 1.1 Gaiia Inventory Summary

| Layer | Database | Count | Type |
| --- | --- | --- | --- |
| Raw Tables (Crawler) | raw_gaiia | 12 | External (JSON) |
| Raw Tables (Manual) | raw_gaiia | 3 | External (JSON/Text) |
| Curated Views (GraphQL) | curated_core | 12 | VIEW |
| Curated Views (Derived) | curated_core | 4 | VIEW |
| Curated Tables | curated_core | 1 | External (Parquet) |
| Exception Views | curated_recon | 3 | VIEW |
| TOTAL |  | 35 |  |

Phase 1: New Account: S3, Crawlers & Catalog Setup

Timeline: W1-W2  |  Resource: R1  |  Est. Hours: 18h

- Create Glue databases: raw_gaiia, curated_core, curated_recon in new account Glue Catalog

- Create Glue Crawler: gaiia-graphql-raw-crawler with 3 data sources (gwi/lymefiber/dvfiber)

  - Configure partition scheme: ingestion_year / ingestion_month / ingestion_day / run_id

  - Set table prefix raw_gaiia_graphql_ targeting raw_gaiia database

  - Validate crawler discovers all 42 entities across all 3 tenants

- Create IAM roles: Glue service role (S3 read on raw bucket), Glue job role (S3 write on curated bucket)

- Design tenant derivation: Tenant is now a top-level folder, not a partition key. Derive tenant column from S3 path in PySpark.

- Run crawler & validate: Verify all entities created, partitions detected, sample data accessible

Phase 2: Curated SQL to Glue PySpark Notebooks

Timeline: W3-W10  |  Resource: R2  |  Est. Hours: 87h

Convert all 19 Athena curated views/tables into Glue PySpark notebooks. Each notebook reads from raw, transforms, and writes Parquet to the new curated S3 bucket.

12 GraphQL Current-State Views (each applies dedup: latest by tenant + id + ingestion date):

| # | Notebook (PySpark) | Replaces View | Reads From |
| --- | --- | --- | --- |
| 1 | gaiia_accounts_current.ipynb | gaiia_accounts_current | raw_gaiia_graphql_accounts_json |
| 2 | gaiia_billing_subscriptions.ipynb | gaiia_billing_subscriptions_current | raw_gaiia_graphql_billingsubscriptions |
| 3 | gaiia_payment_methods.ipynb | gaiia_payment_methods_current | raw_gaiia_graphql_paymentmethods |
| 4 | gaiia_products.ipynb | gaiia_products_current | raw_gaiia_graphql_products |
| 5 | gaiia_properties.ipynb | gaiia_properties_current | raw_gaiia_graphql_properties |
| 6 | gaiia_units.ipynb | gaiia_units_current | raw_gaiia_graphql_units |
| 7 | gaiia_tickets.ipynb | gaiia_tickets_current | raw_gaiia_graphql_tickets |
| 8 | gaiia_work_orders.ipynb | gaiia_work_orders_current | raw_gaiia_graphql_workorders |
| 9 | gaiia_users.ipynb | gaiia_users_current | raw_gaiia_graphql_users |
| 10 | gaiia_inventory_items.ipynb | gaiia_inventory_items_current | raw_gaiia_graphql_inventoryitems |
| 11 | gaiia_inventory_models.ipynb | gaiia_inventory_models_current | raw_gaiia_graphql_inventorymodels |
| 12 | gaiia_inventory_locations.ipynb | gaiia_inventory_locations_current | raw_gaiia_graphql_inventorylocations |

4 Derived Curated Views:

| # | Notebook | Key Logic |
| --- | --- | --- |
| 13 | gaiia_customers_current.ipynb | Reads accounts_current output, flattens fields (plat_id, vetro_id, etc.) |
| 14 | gaiia_invoices_curated_raw.ipynb | Writes Parquet to curated S3 (replaces CTAS) |
| 15 | gaiia_invoices_current.ipynb | Reads curated_raw, dedup + filter error records |
| 16 | gaiia_subscriptions_services.ipynb | JOIN billing_subscriptions + products |

3 Exception Views:

| # | Notebook | Exception Rules |
| --- | --- | --- |
| 17 | gaiia_customers_exceptions.ipynb | missing_account_id, missing_name, missing_tenant |
| 18 | gaiia_invoices_exceptions.ipynb | auth_or_query_error, missing_inputs, empty_record_json |
| 19 | gaiia_subscriptions_services_exceptions.ipynb | missing_subscription_id, missing_product_version_id |

- Glue Workflow: Layer 1 (12 GraphQL, parallel) > Layer 2 (accounts, invoices_raw, subscriptions) > Layer 3 (customers, invoices, exceptions)

- Output: All Parquet files written to new curated S3 bucket, registered as Glue Catalog tables

Phase 3: SSOT SQL to Glue PySpark Notebooks

Timeline: W10-W15  |  Resource: R1  |  Est. Hours: 61h

Convert SSOT core queries and crosswalk/dimension tables from Athena SQL to PySpark notebooks.

SSOT Crosswalk Entities for Gaiia:

| Gaiia Entity | SSOT Crosswalk ID | Links To |
| --- | --- | --- |
| gaiia_account | ssot_account_id | Platt (via plat_id), Vetro (via vetro_id) |
| gaiia_property | ssot_location_id | Physical addresses |
| gaiia_inventory_item | ssot_asset_id | Equipment tracking |
| gaiia_product | ssot_product_id | Service catalog |
| gaiia_subscription | ssot_contract_id | Billing subscriptions |
| gaiia_ticket | ssot_ticket_id | Support tickets |
| gaiia_payment_method | ssot_payment_id | Payment methods |
| gaiia_invoice | ssot_invoice_id | Invoice records |

- Core SSOT: Convert account, customer, invoice, property, ticket, subscription SSOT queries (24h)

- Crosswalks: Convert all 8 xwalk + dim auto-gen tables to PySpark (18h)

- Orchestration: Add SSOT notebooks as Layer 4 in Glue Workflow

- Testing: Validate all 8 SSOT xwalk chains, full raw > curated > SSOT pipeline (10h)

Phase 4: Validation & Documentation

Timeline: W16-W17  |  Resource: R1  |  Est. Hours: 14h

- Data validation: Validate completeness from raw (3 tenants) through to SSOT in new account

- Cross-source checks: Verify Gaiia-Platt crosswalk (plat_id), Gaiia-Vetro crosswalk (vetro_id)

- Documentation: Full Glue pipeline architecture, data lineage, Glue Workflow dependency graph

- Sign-off: Stakeholder approval on Gaiia data quality in new account

GAIIA TOTAL: 180 hours  |  4 Phases  |  17 Weeks

# 2. VETRO

Vetro has no S3 folder structure changes. Data continues in the same format but in the new account and new S3 bucket.

## 2.1 Vetro Inventory Summary

| Layer | Database | Count | Type |
| --- | --- | --- | --- |
| Raw Tables | raw_vetro / gwi_raw | 5 | External (JSON/CSV) |
| Curated Views | curated_core | 17 | VIEW |
| Curated Tables | curated_core | 1 | External (Parquet) |
| Recon Tables/Views | curated_recon | 6 | VIEW + CSV External |
| Legacy CTAS | curated | 1 | PARQUET CTAS |
| TOTAL |  | 30 |  |

## 2.2 Full Curated View List

| # | View/Table Name | Type | Database |
| --- | --- | --- | --- |
| 1 | v_vetro_plans_catalog | VIEW | curated_core |
| 2 | v_vetro_plans_catalog_current | VIEW | curated_core |
| 3 | v_vetro_plans_as_built | VIEW | curated_core |
| 4 | v_vetro_passings_by_plan | VIEW | curated_core |
| 5 | v_vetro_bsl_passings_by_project | VIEW | curated_core |
| 6 | v_passings_bulk_retail_split_vetro_scaffold | VIEW | curated_core |
| 7 | v_vetro_network_map_layers_v1 | VIEW | curated_core |
| 8 | v_vetro_map_lines_layers_v1 | VIEW | curated_core |
| 9 | v_vetro_map_lines_owner_v1 | VIEW | curated_core |
| 10 | v_vetro_map_polygons_v1 | VIEW | curated_core |
| 11 | v_vetro_map_service_locations | VIEW | curated_core |
| 12 | v_vetro_map_naps | VIEW | curated_core |
| 13 | v_vetro_map_fat | VIEW | curated_core |
| 14 | v_vetro_service_locations | VIEW | curated_core |
| 15 | v_vetro_network_map_counts_v1 | VIEW | curated_core |
| 16 | v_vetro_network_plan_xwalk_v1 | VIEW | curated_core |
| 17 | v_vetro_network_plan_xwalk_v2 | VIEW | curated_core |
| 18 | vetro_plan_map | TABLE (Parquet) | curated_core |
| 19 | v_investor_revenue_mix_latest_norm | VIEW | curated_recon |
| 20 | v_vetro_service_locations_ap | VIEW | curated_recon |
| 21 | v_vetro_plan_network_from_ap | VIEW | curated_recon |
| 22 | v_investor_network_mrr_recon_latest | VIEW | curated_recon |
| 23 | curated_vetro_exports | CTAS (Parquet) | curated |

Phase 1: New Account: S3, Crawlers & Catalog Setup

Timeline: W1-W2  |  Resource: R2  |  Est. Hours: 11h

- Create Glue databases: raw_vetro, curated_core entries in new account

- Create Glue Crawler: Vetro raw crawler pointing to new S3 bucket paths

- Create IAM roles: S3 read (raw) + S3 write (curated) for Glue jobs

- Validate: Run crawler, verify entities, test ZIP extraction on new paths

Phase 2: Curated SQL to Glue PySpark Notebooks

Timeline: W3-W8  |  Resource: R2  |  Est. Hours: 58h

Convert all 23 curated views/tables into PySpark notebooks:

- Plan & catalog views: v_vetro_plans_catalog, plans_catalog_current, plans_as_built

- Passings views: v_vetro_passings_by_plan, bsl_passings_by_project, bulk_retail_split

- GIS/Map views: network_map_layers, map_lines_layers, map_lines_owner, map_polygons, service_locations, naps, fat (7 views)

- Network views: network_map_counts, network_plan_xwalk_v1, network_plan_xwalk_v2

- Recon views: investor_revenue_mix, service_locations_ap, plan_network_from_ap, investor_network_mrr_recon

- CTAS replacement: curated_vetro_exports (write Parquet directly)

- ZIP extraction: Implement ZIP extraction logic in PySpark for Vetro-specific data

- Glue Workflow: Orchestrate all notebooks with dependency ordering

Phase 3: SSOT SQL to Glue PySpark Notebooks

Timeline: W8-W14  |  Resource: R1  |  Est. Hours: 53h

- Core SSOT: Convert Vetro plan, network, MRR SSOT queries to PySpark (22h)

- Crosswalks: Convert Vetro-Gaiia crosswalks and dimension tables (15h)

- Orchestration: Add SSOT notebooks to Glue Workflow (4h)

- Testing: Full pipeline: raw > curated > SSOT validation (9h)

Phase 4: Validation & Documentation

Timeline: W15-W17  |  Resource: R1  |  Est. Hours: 11h

- Data validation: Completeness from raw to SSOT in new account

- Cross-source: Verify Vetro-Gaiia crosswalk chains end-to-end

- Documentation: Glue pipeline architecture and data lineage

VETRO TOTAL: 133 hours  |  4 Phases  |  17 Weeks

# 3. INTACCT

Intacct is the financial data source (GL entries). No S3 folder structure changes. Requires finance team coordination and audit trail.

## 3.1 Intacct Inventory Summary

| Layer | Database | Count | Type |
| --- | --- | --- | --- |
| Raw Tables | gwi_raw | 1 | External (JSON) |
| Curated Views | curated_core | 2 | VIEW |
| CTAS Tables | curated | 1 | PARQUET CTAS (dt partitioned) |
| Exception Views | curated_recon | 1 | VIEW |
| Finance Views | curated_finance | 2 | VIEW |
| TOTAL |  | 7 |  |

## 3.2 Full Entity List

| # | Name | Type | Database | Availability | Raw Table(s) Used | File Path |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | raw_intacct_gl_entries | RAW TABLE (JSON) | gwi_raw | present | N/A (is the raw source) | lake_deploy/athena/raw/legacy_ddls/raw_intacct_gl_entries.sql |
| 2 | curated_intacct_gl_entries | CTAS (Parquet, dt partitioned) | curated | Not available | gwi_raw.raw_intacct_gl_entries | lake_deploy/athena/curated/legacy_ctas/curated_intacct_gl_entries.sql |
| 3 | intacct_gl_entries_curated_raw | VIEW | curated_core | present | gwi_raw.raw_intacct_gl_entries | Not defined in repo (legacy Athena view) |
| 4 | intacct_gl_entries_current_ssot | VIEW | curated_core | present | curated_core.intacct_gl_entries_curated_raw; curated_finance.coa_accounts_latest; curated_finance.sage_dimensions_latest | lake_deploy/athena/curated/ssot/40_ssot_intacct_gl_entries.sql; 41_ssot_intacct_enrichment.sql |
| 5 | intacct_gl_entries_exceptions | VIEW | curated_recon | present | curated_core.intacct_gl_entries_curated_raw | lake_deploy/athena/curated/ssot/40_ssot_intacct_gl_entries.sql |
| 6 | coa_accounts_latest | VIEW | curated_finance | present | curated_finance.coa_accounts | lake_deploy/athena/curated/ssot/41_ssot_intacct_enrichment.sql |
| 7 | sage_dimensions_latest | VIEW | curated_finance | present | curated_finance.sage_dimensions | lake_deploy/athena/curated/ssot/41_ssot_intacct_enrichment.sql |

Phase 1: New Account: S3, Crawlers & Catalog Setup

Timeline: W1-W2  |  Resource: R1  |  Est. Hours: 18h

- Create Glue databases: gwi_raw (or raw_intacct), curated, curated_core, curated_recon, curated_finance

- Create Terraform modules: Glue crawlers, databases, IAM roles, S3 bucket policies (5h)

- Create IAM roles: Glue service role + job execution role for new account

- Finance team coordination: Coordinate data availability expectations in new account

- Run crawler & validate: Verify GL entry tables created, data accessible

Phase 2: Curated SQL to Glue PySpark Notebooks

Timeline: W3-W9  |  Resource: R2  |  Est. Hours: 59h

Convert all 7 curated objects into PySpark notebooks:

| # | Notebook | Replaces | Key Logic |
| --- | --- | --- | --- |
| 1 | intacct_gl_entries_curated.ipynb | curated_intacct_gl_entries (CTAS) | Read raw JSON, transform, write Parquet with dt partition |
| 2 | intacct_gl_entries_curated_raw.ipynb | intacct_gl_entries_curated_raw | Curated raw view logic |
| 3 | intacct_gl_entries_current_ssot.ipynb | intacct_gl_entries_current_ssot | SSOT-ready GL entries |
| 4 | intacct_gl_entries_exceptions.ipynb | intacct_gl_entries_exceptions | Data quality exception rules |
| 5 | coa_accounts_latest.ipynb | coa_accounts_latest | Chart of accounts latest snapshot |
| 6 | sage_dimensions_latest.ipynb | sage_dimensions_latest | Sage dimension latest snapshot |
| 7 | xml_to_json_transform.ipynb | Custom logic | XML-to-JSON transformation in PySpark |

- Financial validation: Finance team review of Glue PySpark output accuracy, GL total reconciliation (10h)

- Glue Workflow: Orchestrate notebooks with dependency ordering + triggers

Phase 3: SSOT SQL to Glue PySpark Notebooks

Timeline: W9-W15  |  Resource: R1  |  Est. Hours: 78h

- Core SSOT: Convert GL entries, enrichment, revenue mix, unit economics SSOT queries (30h)

- Crosswalks: Convert SF-Intacct crosswalk files, multi-source crosswalks, auto-gen xwalk/dim (22h)

- Audit trail: Financial data reconciliation checks + audit trail in new curated bucket (8h)

- Finance sign-off: Full pipeline testing with finance team approval (10h)

Phase 4: Validation & Documentation

Timeline: W16-W17  |  Resource: R1  |  Est. Hours: 13h

- Financial validation: GL entry data completeness, financial totals reconciliation

- Cross-source: Verify SF-Intacct and Platt-Intacct crosswalk chains

- Finance sign-off: Final approval + audit trail documentation

INTACCT TOTAL: 168 hours  |  4 Phases  |  17 Weeks

# 4. SALESFORCE

Salesforce data is ingested via AppFlow. No S3 folder structure changes. Accounts and opportunities are the primary entities.

## 4.1 Salesforce Inventory Summary

| Layer | Database | Count | Type |
| --- | --- | --- | --- |
| Raw Tables | gwi_raw / raw_salesforce_direct | 3 | External (CSV/JSON) |
| Curated Views | raw_salesforce | 1 | VIEW |
| CTAS Tables | curated | 2 | PARQUET CTAS |
| TOTAL |  | 6 |  |

## 4.2 Full Entity List

| # | Name | Type | Database |
| --- | --- | --- | --- |
| 1 | raw_salesforce_accounts | RAW TABLE (CSV) | gwi_raw |
| 2 | raw_salesforce_opportunities | RAW TABLE (CSV) | gwi_raw |
| 3 | account_guarantor | RAW TABLE (JSON) | raw_salesforce_direct |
| 4 | v_account_segment | VIEW | raw_salesforce |
| 5 | curated_salesforce_accounts | CTAS (Parquet) | curated |
| 6 | curated_salesforce_opportunities | CTAS (Parquet) | curated |

Phase 1: New Account: S3, Crawlers & Catalog Setup

Timeline: W1-W2  |  Resource: R2  |  Est. Hours: 11h

- Create Glue databases: gwi_raw (or raw_salesforce), raw_salesforce_direct, curated entries

- Create Glue Crawler: SF raw crawler pointing to new S3 bucket

- Configure AppFlow: Set up AppFlow destination in new account bucket

- Create IAM roles: Glue + AppFlow execution roles

- Validate: Run crawler, verify AppFlow delivery to new bucket

Phase 2: Curated SQL to Glue PySpark Notebooks

Timeline: W3-W8  |  Resource: R2  |  Est. Hours: 45h

| # | Notebook | Replaces | Key Logic |
| --- | --- | --- | --- |
| 1 | salesforce_accounts_curated.ipynb | curated_salesforce_accounts (CTAS) | Read raw CSV, transform, write Parquet with dt partition |
| 2 | salesforce_opportunities_curated.ipynb | curated_salesforce_opportunities (CTAS) | Read raw CSV, transform, write Parquet with dt partition |
| 3 | salesforce_account_segment.ipynb | v_account_segment | Account segmentation logic |
| 4 | salesforce_account_guarantor.ipynb | account_guarantor (raw processing) | Guarantor mapping from SF direct |

- Glue Workflow: Orchestrate notebooks with dependency ordering

- Testing: Account/opportunity data quality validation (8h)

Phase 3: SSOT SQL to Glue PySpark Notebooks

Timeline: W8-W14  |  Resource: R1  |  Est. Hours: 58h

- Core SSOT: Convert SF account, opportunity SSOT queries (24h)

- Crosswalks: Convert SF-Intacct crosswalks, multi-source xwalks, auto-gen dim tables (18h)

- Orchestration: Add SSOT notebooks to Glue Workflow (4h)

- Testing: Full pipeline validation for all SF entities (9h)

Phase 4: Validation & Documentation

Timeline: W15-W17  |  Resource: R1  |  Est. Hours: 10h

- Data validation: SF data completeness from raw to SSOT

- Cross-source: Verify SF-Intacct crosswalk chains

- Documentation: Pipeline architecture + data lineage

SALESFORCE TOTAL: 124 hours  |  4 Phases  |  17 Weeks

# 5. PLATT

Platt is the legacy billing system. No S3 folder structure changes. Includes custom SerDe handling (pipe-delimited and unit-separator delimited files).

## 5.1 Platt Inventory Summary

| Layer | Database | Count | Type |
| --- | --- | --- | --- |
| Raw Tables (pipe-delimited) | raw_platt | 5 | External (CSV, custom SerDe) |
| Raw Tables (unit-sep) | raw_platt | 1 | External (as_billed, USV) |
| Raw Tables (ops) | raw_platt | 4 | External (CSV) |
| Raw Tables (other) | gwi_raw | 1 | External (CSV) |
| Curated Views | curated_core | 11 | VIEW |
| Exception Views | curated_recon | 1 | VIEW |
| Crosswalk CTAS | curated_crosswalks | 1 | PARQUET CTAS |
| TOTAL |  | 24 |  |

## 5.2 Full Curated View List

| # | Name | Type | Database |
| --- | --- | --- | --- |
| 1 | v_platt_billing_mrr_monthly | VIEW | curated_core |
| 2 | v_platt_billing_customer_month_latest | VIEW | curated_core |
| 3 | platt_customer_curated_raw | VIEW | curated_core |
| 4 | platt_customer_current_ssot | VIEW | curated_core |
| 5 | v_monthly_mrr_platt_movement | VIEW | curated_core |
| 6 | v_monthly_mrr_platt_movement_enriched | VIEW | curated_core |
| 7 | v_monthly_mrr_platt_movement_enriched_clean | VIEW | curated_core |
| 8 | v_monthly_mrr_platt_movement_segmented | VIEW | curated_core |
| 9 | v_monthly_mrr_by_segment | VIEW | curated_core |
| 10 | v_monthly_account_churn_by_segment | VIEW | curated_core |
| 11 | v_monthly_mrr_and_churn_summary | VIEW | curated_core |
| 12 | platt_customer_exceptions | VIEW | curated_recon |
| 13 | platt_as_billed_24m_parquet | CTAS (Parquet) | curated_core |
| 14 | platt_to_intacct_customer_1to1 | CTAS (Parquet) | curated_crosswalks |

Phase 1: New Account: S3, Crawlers & Catalog Setup

Timeline: W1-W2  |  Resource: R2  |  Est. Hours: 7h

- Create Glue databases: raw_platt, curated_core, curated_recon, curated_crosswalks

- Create Glue Crawler: Platt raw crawler for new S3 bucket

- Validate: Run crawler, verify entities, confirm as-billed 24m data

Phase 2: Curated SQL to Glue PySpark Notebooks

Timeline: W4-W7  |  Resource: R2  |  Est. Hours: 30h

Convert all 14 curated objects into PySpark notebooks:

- Billing/MRR views: v_platt_billing_mrr_monthly, billing_customer_month_latest, monthly_mrr_platt_movement (+ enriched, clean, segmented)

- Customer views: platt_customer_curated_raw, platt_customer_current_ssot

- Summary views: v_monthly_mrr_by_segment, v_monthly_account_churn_by_segment, v_monthly_mrr_and_churn_summary

- CTAS replacements: platt_as_billed_24m_parquet (write Parquet), platt_to_intacct_customer_1to1

- Custom SerDe: Handle pipe-delimited and unit-separator delimited files in PySpark reads

Phase 3: SSOT SQL to Glue PySpark Notebooks

Timeline: W8-W12  |  Resource: R1  |  Est. Hours: 33h

- Core SSOT: Convert Platt billing, circuit master SSOT queries (14h)

- Crosswalks: Convert Platt-Intacct, Platt-Gaiia crosswalks (10h)

- Testing: Full pipeline testing for all Platt entities (5h)

Phase 4: Validation & Documentation

Timeline: W15-W17  |  Resource: R1  |  Est. Hours: 8h

- Data validation: As-billed data completeness from raw to SSOT

- Cross-source: Verify Platt-Intacct and Platt-Gaiia crosswalks

- Documentation: Pipeline architecture + data lineage

PLATT TOTAL: 78 hours  |  4 Phases  |  17 Weeks

# Grand Summary

| Metric | Value |
| --- | --- |
| Total Sources | 5 (Gaiia, Vetro, Platt, Intacct, Salesforce) |
| Total Hours | 683h |
| Timeline | 17 Weeks |
| Resources | 2 |
| Athena Usage | NONE |
| Cross-Account Access | NONE |
| Output Format | Parquet to new curated S3 bucket |
| Orchestration | Glue Workflows per source |
| Catalog | Glue Data Catalog (new account) |
| S3 Structure Change | Gaiia only (3 tenants, new partitions) |